## Code Contributions
Summary of Contributions
| Serial number | Module | File Name | Method Name | Author | Member | Number of Modules
| 1 | Ride-Share | src/main/java/com/tripmanagement/asdc/controller/CustomerController.java | searchRides | Sanika Tamhankar | Benny Daniel | 9
| 2 |  |  | bookRide |  | Dharmay Sureja | 9
| 3 |  |  | openCredit |  | Prakrut Suthar | 9
| 4 | Authentication | src/main/java/com/tripmanagement/asdc/controller/RegistrationController.java | userLogin | Dharmay Sureja | Sanika Tamhankar | 9
| 5 |  |  | forgotPassword |  | Vatsal Yadav | 9
| 6 |  |  | registerUser
| 7 | Vehicle Management | src/main/java/com/tripmanagement/asdc/controller/VehicleController.java | addTripDetails | Vatsal Yadav
| 8 |  |  | testController
| 9 | Vehicle Management | src/main/java/com/tripmanagement/asdc/controller/VehicleOwnerController.java | createRide | Vatsal Yadav
| 10 |  |  | addVehicle
| 11 |  |  | deleteVehicle
| 12 |  |  | openCredit
| 13 | Ride-Share | src/main/java/com/tripmanagement/asdc/dao/BookingDAO.java | saveRide | Benny Daniel
| 14 |  |  | getAllRidesForCustomer
| 15 |  |  | updateIsPaid
| 16 | Ride-Share | src/main/java/com/tripmanagement/asdc/dao/BookingDAOImpl.java | saveRide | Benny Daniel
| 17 |  |  | getAllRidesForCustomer
| 18 |  |  | updateIsPaid
| 19 | Ride-Share | src/main/java/com/tripmanagement/asdc/dao/CustomerDAO.java | saveCustomer | Sanika Tamhankar
| 20 |  |  | getCustomerByEmail
| 21 |  |  | getCustomerById
| 22 |  |  | updateAvaialableCredits
| 23 | Ride-Share | src/main/java/com/tripmanagement/asdc/dao/CustomerDAOImpl.java | saveCustomer | Sanika Tamhankar
| 24 |  |  | getCustomerByEmail
| 25 |  |  | getCustomerById
| 26 |  |  | updateAvaialableCredits
| 27 | Fuel Economy Calculation | src/main/java/com/tripmanagement/asdc/dao/FuelEconomyDAO.java | FuelEconomyDAO | Benny Daniel
| 28 |  | src/main/java/com/tripmanagement/asdc/dao/FuelEconomyDAOImpl.java | saveFuelEconomy | Benny Daniel
| 29 |  | src/main/java/com/tripmanagement/asdc/dao/RegistrationDAO.java | checkUserExistByEmail | Dharmay Sureja
| 30 |  |  | checkEmailExists
| 31 |  |  | checkEmailPassword
| 32 | Authentication | src/main/java/com/tripmanagement/asdc/dao/RegistrationDAOImpl.java | checkUserExistByEmail | Dharmay Sureja
| 33 |  |  | checkEmailPassword
| 34 |  |  | checkEmailExists
| 35 | Trip Analysis | src/main/java/com/tripmanagement/asdc/dao/TripDAO.java | saveTrip | Benny Daniel
| 36 |  |  | getTripDetails
| 37 |  |  | getAllTripsForVehicleOwner
| 38 |  |  | deleteTrip
| 39 |  |  | getAvailableTripsList
| 40 |  |  | getSources
| 41 |  |  | getDestinations
| 42 |  |  | updateAvailableSeats
| 43 | Trip Analysis | src/main/java/com/tripmanagement/asdc/dao/TripDAOmpl.java | saveTrip | Benny Daniel
| 44 |  |  | getTripDetails
| 45 |  |  | getAllTripsForVehicleOwner
| 46 |  |  | deleteTrip
| 47 |  |  | getAvailableTripsList
| 48 |  |  | getSources
| 49 |  |  | getDestinations
| 50 |  |  | updateAvailableSeats
| 51 | Vehicle Management | src/main/java/com/tripmanagement/asdc/dao/VehicleDAO.java | addVehicle | Vatsal Yadav
| 52 |  |  | getVehicleDetails
| 53 |  |  | getVehicles
| 54 |  |  | updateVehicleFuelEconomy
| 55 |  |  | deleteVehicle
| 56 | Vehicle Management | src/main/java/com/tripmanagement/asdc/dao/VehicleDAOImpl.java | addVehicle | Vatsal Yadav
| 57 |  |  | getVehicleDetails
| 58 |  |  | getVehicles
| 59 |  |  | updateVehicleFuelEconomy
| 60 |  |  | deleteVehicle
| 61 | Vehicle Management | src/main/java/com/tripmanagement/asdc/dao/VehicleOwnerDAO.java | saveVehicleOwner | Prakrut Suthar
| 62 |  |  | getVehicleOwnerByEmail
| 63 |  |  | getVehicleOwnerById
| 64 |  |  | updateAvaialableCredits
| 65 | Vehicle Management | src/main/java/com/tripmanagement/asdc/dao/VehicleOwnerDAOImpl.java | saveVehicleOwner | Prakrut Suthar
| 66 |  |  | getVehicleOwnerByEmail
| 67 |  |  | getVehicleOwnerById
| 68 |  |  | updateAvaialableCredits
| 69 | Ride-Share | src/main/java/com/tripmanagement/asdc/model/Booking.java | Booking | Sanika Tamhankar
| 70 |  |  | getBooked_ride_id
| 71 |  |  | setBooked_ride_id
| 72 |  |  | getCustomer_id
| 73 |  |  | setCustomer_id
| 74 |  |  | getTimestamp
| 75 |  |  | setTimestamp
| 76 |  |  | getCost
| 77 |  |  | setCost
| 78 |  |  | getSeats_booked
| 79 |  |  | setSeats_booked
| 80 |  |  | getTrip_id
| 81 |  |  | setTrip_id
| 82 |  |  | getIsPaid
| 83 |  |  | setIsPaid
| 84 |  |  | toString
| 85 | Ride-Share | src/main/java/com/tripmanagement/asdc/model/Customer.java | Customer | Sanika Tamhankar
| 86 |  |  | getCustomer_id
| 87 |  |  | setCustomer_id
| 88 |  |  | getCustomer_lname
| 89 |  |  | setCustomer_lname
| 90 |  |  | getMobile_no
| 91 |  |  | setMobile_no
| 92 |  |  | getEmail
| 93 |  |  | getCustomer_fname
| 94 |  |  | setCustomer_fname
| 95 |  |  | setEmail
| 96 |  |  | getPassword
| 97 |  |  | setPassword
| 98 |  |  | getAvailable_credits
| 99 |  |  | setAvailable_credits
| 100 |  |  | toString
| 101 | Fuel Economy Calculation | src/main/java/com/tripmanagement/asdc/model/FuelEconomy.java | FuelEconomy | Benny Daniel
| 102 |  |  | getTrip_history_id
| 103 |  |  | setTrip_history_id
| 104 |  |  | getTrip_id
| 105 |  |  | setTrip_id
| 106 |  |  | getKms_travelled
| 107 |  |  | setKms_travelled
| 108 |  |  | getFuel_consumed
| 109 |  |  | setFuel_consumed
| 110 |  |  | getFuel_economy
| 111 |  |  | setFuel_economy
| 112 |  |  | getTimestamp
| 113 |  |  | setTimestamp
| 114 |  |  | getVehicle_id
| 115 |  |  | setVehicle_id
| 116 |  |  | toString
| 117 | Payment | src/main/java/com/tripmanagement/asdc/model/Payment.java | Payment | Sanika Tamhankar
| 118 |  |  | getPayment_id
| 119 |  |  | setPayment_id
| 120 |  |  | getVehicleowner_id
| 121 |  |  | setVehicleowner_id
| 122 |  |  | getAmount
| 123 |  |  | setAmount
| 124 |  |  | getTrip_id
| 125 |  |  | setTrip_id
| 126 |  |  | getTimestamp
| 127 |  |  | setTimestamp
| 128 |  |  | toString
| 129 | Ride-Share | src/main/java/com/tripmanagement/asdc/model/Ride.java | Ride | Benny Daniel
| 130 |  |  | getNumberPlate
| 131 |  |  | setNumberPlate
| 132 |  |  | getVehicleOwnerId
| 133 |  |  | setVehicleOwnerId
| 134 |  |  | getAvailableSeats
| 135 |  |  | setAvailableSeats
| 136 |  |  | getTrip
| 137 |  |  | setTrip
| 138 |  |  | getVehicle_id
| 139 |  |  | setVehicle_id
| 140 |  |  | getFuel_economy
| 141 |  |  | setFuel_economy
| 142 |  |  | getVehicleOwnerName
| 143 |  |  | setVehicleOwnerName
| 144 |  |  | getPhone
| 145 |  |  | setPhone
| 146 |  |  | getCost
| 147 |  |  | setCost
| 148 | Trip Analysis | src/main/java/com/tripmanagement/asdc/model/Trip.java | Trip | Prakrut Suthar
| 149 |  |  | getTrip_id
| 150 |  |  | setTrip_id
| 151 |  |  | getSource
| 152 |  |  | setSource
| 153 |  |  | getDestination
| 154 |  |  | setDestination
| 155 |  |  | getVehicle_id
| 156 |  |  | setVehicle_id
| 157 |  |  | getEstimated_kms
| 158 |  |  | setEstimated_kms
| 159 |  |  | getKms_travelled
| 160 |  |  | setKms_travelled
| 161 |  |  | getAvailable_seats
| 162 |  |  | setAvailable_seats
| 163 |  |  | getStart_time
| 164 |  |  | setStart_time
| 165 |  |  | getEnd_time
| 166 |  |  | setEnd_time
| 167 |  |  | getSeats_remaining
| 168 |  |  | setSeats_remaining
| 169 |  |  | getCost
| 170 |  |  | setCost
| 171 |  |  | getVehicle_owner_id
| 172 |  |  | setVehicle_owner_id
| 173 | Ride-Share | src/main/java/com/tripmanagement/asdc/model/User.java | User | Dharmay Sureja
| 174 |  |  | getEmail
| 175 |  |  | setEmail
| 176 |  |  | getPassword
| 177 |  |  | setPassword
| 178 |  |  | getUserType
| 179 |  |  | setUserType
| 180 |  |  | getFirst_name
| 181 |  |  | setFirst_name
| 182 |  |  | getLast_name
| 183 |  |  | setLast_name
| 184 | Authentication | src/main/java/com/tripmanagement/asdc/model/Vehicle.java | Vehicle | Dharmay Sureja
| 185 |  |  | getTrips
| 186 |  |  | setTrips
| 187 |  |  | getFuel_economy
| 188 |  |  | setFuel_economy
| 189 |  |  | getVehicle_id
| 190 |  |  | setVehicle_id
| 191 |  |  | getVehicleowner_id
| 192 |  |  | setVehicleowner_id
| 193 |  |  | getNumber_plate
| 194 |  |  | setNumber_plate
| 195 |  |  | getVehicle_name
| 196 |  |  | setVehicle_name
| 197 |  |  | getType
| 198 |  |  | setType
| 199 |  |  | getKms_driven
| 200 |  |  | setKms_driven
| 201 |  |  | getAvailable_seats
| 202 |  |  | setAvailable_seats
| 203 |  |  | getFuel_consumed
| 204 |  |  | setFuel_consumed
| 205 |  |  | getBrand
| 206 |  |  | setBrand
| 207 |  |  | getFuel_economy_status
| 208 |  |  | toString
| 209 | Vehicle Management | src/main/java/com/tripmanagement/asdc/model/VehicleOwner.java | VehicleOwner | Vatsal Yadav
| 210 |  |  | getVehicleowner_fname
| 211 |  |  | setVehicleowner_fname
| 212 |  |  | getVehicleowner_lname
| 213 |  |  | setVehicleowner_lname
| 214 |  |  | getPhone
| 215 |  |  | setPhone
| 216 |  |  | getEmail
| 217 |  |  | setEmail
| 218 |  |  | getVehicleOwner_id
| 219 |  |  | setVehicleOwner_id
| 220 |  |  | getPassword
| 221 |  |  | setPassword
| 222 |  |  | getAvailable_credits
| 223 |  |  | setAvailable_credits
| 224 |  |  | toString
| 225 | Ride-Share | src/main/java/com/tripmanagement/asdc/service/BookingService.java | saveRide | Dharmay Sureja
| 226 |  |  | getUpcomingRidesForCustomer
| 227 |  |  | getPreviousRidesForCustomer
| 228 |  |  | updateIsPaid
| 229 |  |  | payforRide
| 230 | Ride-Share | src/main/java/com/tripmanagement/asdc/service/BookingServiceImpl.java | saveRide | Dharmay Sureja
| 231 |  |  | getUpcomingRidesForCustomer
| 232 |  |  | getPreviousRidesForCustomer
| 233 |  |  | updateIsPaid
| 234 |  |  | payforRide
| 235 |  |  | getCurrentTime
| 236 | Authentication | src/main/java/com/tripmanagement/asdc/service/CustomerService.java | saveCustomer | Prakrut Suthar
| 237 |  |  | getCustomerByEmail
| 238 |  |  | getCustomerById
| 239 |  |  | buyCredits
| 240 | Authentication | src/main/java/com/tripmanagement/asdc/service/CustomerServiceImpl.java | saveCustomer | Prakrut Suthar
| 241 |  |  | getCustomerByEmail
| 242 |  |  | getCustomerById
| 243 |  |  | buyCredits
| 244 | Notification | src/main/java/com/tripmanagement/asdc/service/NotificationService.java | sendEmail | Prakrut Suthar
| 245 | Notification | src/main/java/com/tripmanagement/asdc/service/NotificationServiceImpl.java | sendEmail | Sanika Tamhankar
| 246 | Authentication | src/main/java/com/tripmanagement/asdc/service/RegistrationService.java | checkEmailPassword | Sanika Tamhankar
| 247 |  |  | checkUserExistByEmail
| 248 | Authentication | src/main/java/com/tripmanagement/asdc/service/RegistrationServiceImpl.java | checkEmailPassword | Dharmay Sureja
| 249 |  |  | checkUserExistByEmail
| 250 | Trip Analysis | src/main/java/com/tripmanagement/asdc/service/TripService.java | saveTrip | Vatsal Yadav
| 251 |  |  | getTripDetails
| 252 |  |  | getUpcomingTripsForVehicleOwner
| 253 |  |  | getPreviousTripsForVehicleOwner
| 254 |  |  | deleteTrip
| 255 |  |  | getAvailableTripsList
| 256 |  |  | calculateCost
| 257 |  |  | getSources
| 258 |  |  | getDestinations
| 259 | Trip Analysis | src/main/java/com/tripmanagement/asdc/service/TripServiceImpl.java | saveTrip | Vatsal Yadav
| 260 |  |  | getTripDetails
| 261 |  |  | getUpcomingTripsForVehicleOwner
| 262 |  |  | getPreviousTripsForVehicleOwner
| 263 |  |  | deleteTrip
| 264 |  |  | getAvailableTripsList
| 265 |  |  | calculateCost
| 266 |  |  | getSources
| 267 |  |  | getDestinations
| 268 |  |  | getCurrentTime
| 269 | Vehicle Management | src/main/java/com/tripmanagement/asdc/service/VehicleOwnerService.java | saveVehicleOwner | Prakrut Suthar
| 270 |  |  | getVehicleOwnerByEmail
| 271 |  |  | getVehicleOwnerByOwnerId
| 272 |  |  | buyCredits
| 273 | Vehicle Management | src/main/java/com/tripmanagement/asdc/service/VehicleOwnerServiceImpl.java | saveVehicleOwner | Prakrut Suthar
| 274 |  |  | getVehicleOwnerByEmail
| 275 |  |  | getVehicleOwnerByOwnerId
| 276 |  |  | buyCredits
| 277 | Vehicle Management | src/main/java/com/tripmanagement/asdc/service/VehicleService.java | addVehicle | Vatsal Yadav
| 278 |  |  | getVehicleDetails
| 279 |  |  | getVehicles
| 280 |  |  | updateFuelEconomy
| 281 |  |  | setFuel_economy
| 282 |  |  | deleteVehicle
| 283 |  |  | saveFuelEconomy
| 284 | Vehicle Management | src/main/java/com/tripmanagement/asdc/service/VehicleServiceImpl.java | addVehicle | Vatsal Yadav
| 285 |  |  | getVehicleDetails
| 286 |  |  | getVehicles
| 287 |  |  | updateFuelEconomy
| 288 |  |  | setFuel_economy
| 289 |  |  | deleteVehicle
| 290 |  |  | saveFuelEconomy
| 291 |  | src/main/java/com/tripmanagement/asdc/stringsAndConstants/Constants.java |  | Prakrut Suthar
| 292 |  | src/main/java/com/tripmanagement/asdc/stringsAndConstants/FuelEconomyStatus.java |  | Benny Daniel
| 293 |  | src/main/java/com/tripmanagement/asdc/stringsAndConstants/StringMessages.java |  | Sanika Tamhankar
| 294 |  | src/main/java/com/tripmanagement/asdc/AsdcApplication.java | main | Dharmay Sureja

## GitLab
Number of Commits
Total Number of Branches
Total Number of Pull Requests

## JIRA
Summary | Issue key | Issue id | Issue Type | Status | Project key | Project name | Project type | Project lead | Project lead id | Project description | Priority | Resolution | Assignee | Assignee Id | Reporter | Reporter Id | Creator | Creator Id | Created | Updated | Last Viewed | Resolved | Due date | Votes | Labels | Labels2 | Labels3 | Description | Environment | Watchers | Watchers Id | Log Work | Log Work4 | Log Work5 | Log Work6 | Log Work7 | Log Work8 | Log Work9 | Log Work10 | Log Work11 | Log Work12 | Log Work13 | Log Work14 | Log Work15 | Original estimate | Remaining Estimate | Time Spent | Work Ratio | Î£ Original Estimate | Î£ Remaining Estimate | Î£ Time Spent | Security Level | Custom field (Acceptance Criteria) | Custom field (Development) | Custom field (Issue color) | Custom field (Rank) | Sprint | Custom field (Start date) | (Story point estimate) | Comment | Parent | Parent summary | Status Category
Prepare Documentation for the Application | TMP-79 | 10078 | Story | In Progress | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-03-21 15:11 | 2022-04-02 20:56 | 2022-03-21 15:12 |  |  | 0 | Documentation |  |  |  |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | [22 empty] | {} |  | 0¦i000e3: | TMP Sprint 5 |  | 5 |  | 10000 | Trip Management - Web Application | In Progress
Ride Share User Booking Backend and API | TMP-61 | 10060 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | Vatsal Yadav | 61eaf1e0eb1fb60071cf9d29 | Vatsal Yadav | 61eaf1e0eb1fb60071cf9d29 | 2022-03-10 17:50 | 2022-04-02 17:44 | 2022-04-02 17:42 | 2022-04-02 17:44 |  | 0 | [5 empty] | Vatsal Yadav | 61eaf1e0eb1fb60071cf9d29 | Service Layer Implementation for Ride Sharing;02/Apr/22 5:42 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;28800 | DAO layer Implementation for the Ride Share module;02/Apr/22 5:43 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;28800 | Controller for the Ride Share Module and Test activities;02/Apr/22 5:44 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;28800 | [11 empty] | 0 | 86400 |  |  | 0 | 86400 |  |  | {} |  | 0¦i0008f:9 | TMP Sprint 4 |  | 3 |  | 10000 | Trip Management - Web Application | Done | Member | Number of Stories | Story Points
Fuel Economy Calculation Module | TMP-31 | 10030 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | amudgal | 61f7ee1aaab3620070f4b803 | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-02-15 18:15 | 2022-02-28 18:02 | 2022-03-01 23:21 | 2022-02-28 18:02 |  | 0 | Functionality |  |  | Develop a module to determine the fuel efficiency of each vehicle, provided that a vehicle owner inputs, Distance traversed and Fuel consumed. |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | Updated table structure for the Fuel Economy module.;23/Feb/22 5:33 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;14400 | ;24/Feb/22 7:48 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;10800 | Development of the UI for the Fuel Economy Module;28/Feb/22 5:56 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;28800 | Tests for the Fuel Economy Module;28/Feb/22 5:56 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;21600 | [10 empty] | 0 | 75600 |  |  | 0 | 162000 |  | Based on the input, the user should be able to get the fuel economy. | {} |  | 0¦i0005z: | TMP Sprint 2 |  | 3 |  | 10000 | Trip Management - Web Application | Done | Benny Daniel T. | 7 | 21 | Note: The stories listed here are parents. Most parent stories have been broken down into child issues.
Develop code for analyzing the attributes of a Trip in the application | TMP-29 | 10028 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | Ankush Mudgal | 61f07bf2138863006aa1d85f | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-02-15 18:05 | 2022-04-02 17:41 | 2022-04-02 17:37 | 2022-04-02 17:41 |  | 0 | Functionality |  |  | Obtain Trip Summary information subsequent to the completion of each trip. |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | Analysis of Trip Attributes;02/Apr/22 5:38 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;21600 | Model for Trip Attributes;02/Apr/22 5:39 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;28800 | Implementation of Trip Summary Information display;02/Apr/22 5:40 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;28800 | Analysis and Peer Review;02/Apr/22 5:41 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;7200 | [10 empty] | 0 | 86400 |  |  | 0 | 86400 |  | After a trip has been completed, the user should get a summary of his/her trip(distance traveled, fuel consumed). | {} |  | 0¦i0008f:i | TMP Sprint 4 |  | 3 |  | 10000 | Trip Management - Web Application | Done | Dharmay Sureja | 7 | 21
Implement Continuous Code Quality Analysis in GitLab | TMP-23 | 10022 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | Ankush Mudgal | 61f07bf2138863006aa1d85f | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-02-10 17:41 | 2022-03-17 00:06 | 2022-03-14 17:18 | 2022-03-17 00:06 |  | 0 | Configuration |  |  | Establish connectivity between GitLab, Qscored and Designite. |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | Included script to generate a XML file through DesigniteJava. Generated API key for access to QScored.;03/Mar/22 6:39 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;7200 | ;03/Mar/22 6:44 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;10800 | Modified the command to execute DesigniteJava. Used -ci instead of -f XML.;14/Mar/22 5:16 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;14400 | Tested the Pipeline.;14/Mar/22 5:17 PM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;7200 | [10 empty] | 0 | 39600 |  |  | 0 | 97200 |  | *Qscored* and *Designite* should be set up. Code Quality Reports should be available for the Source Code associated with the project. | {} |  | 0¦i0008j: | TMP Sprint 3 |  | 3 |  | 10000 | Trip Management - Web Application | Done | Prakrut Suthar | 6 | 21
JIRA Board Configuration | TMP-16 | 10015 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | amudgal | 61f7ee1aaab3620070f4b803 | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-02-03 00:24 | 2022-02-10 18:50 | 2022-04-03 13:40 | 2022-02-03 00:39 |  | 0 | Issue_Tracker |  |  | User Story for the setup and configuration of a Jira board, creation of the initial user stories. |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | ;03/Feb/22 12:37 AM;ug:0e1b4443-21e5-4b32-a4c3-478b50f7c0d3;14400 | [13 empty] | 0 | 14400 |  |  | 0 | 14400 |  | # A Jira board to track issues and tasks associated with the project - Trip Management System must be setup. # Appropriate access must be granted to all personnel involved in the development of the project and a few stakeholders. # The parameters associated with the board must be updated appropriately. | {} |  | 0¦i0000r: | TMP Sprint 1 |  | 1 | 03/Feb/22 12:32 AM;61eaf0597ae0dc006ac957d6;A Jira board has been setup and appropriate access privileges have been granted to relevant personnel. Note: {color:#ff5630}*Each Sprint lasts for two weeks*{color} {color:#ff5630}*Each Story Point represents 8 Hours (OR) 1 Day.*{color} | 10000 | Trip Management - Web Application | Done | Sanika Tamhankar | 6 | 21
Create a CI/CD Pipeline for the Project | TMP-3 | 10002 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | amudgal | 61f7ee1aaab3620070f4b803 | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-01-31 10:21 | 2022-02-14 23:56 | 2022-03-01 23:24 | 2022-02-14 23:56 |  | 0 | Configuration |  |  | User Story for the creation of a Continuous Integration and development pipeline in GitLab. |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | [18 empty] | 9000 | 113400 |  | A CI/CD pipeline with successful runs for builds & tests should be available. Working git-config file must be added to the Repository. | {} |  | 0¦i00006: | TMP Sprint 1 |  | 3 |  | 10000 | Trip Management - Web Application | Done | Vatsal Yadav | 8 | 21
Bugfixes_database | TMP-68 | 10067 | Story | In Progress | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium |  | Dharmay Sureja | 61eaf1e15fcc370068978971 | Dharmay Sureja | 61eaf1e15fcc370068978971 | Dharmay Sureja | 61eaf1e15fcc370068978971 | 2022-03-21 14:40 | 2022-04-02 20:56 | 2022-04-03 13:44 |  |  | 0 |  |  |  | Bug fixes for database |  | Dharmay Sureja | 61eaf1e15fcc370068978971 | [22 empty] | {} |  | 0¦i000dl: | TMP Sprint 5 |  | 3 |  | 10000 | Trip Management - Web Application | In Progress
Integration and merging of all features | TMP-64 | 10063 | Story | In Progress | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium |  | Dharmay Sureja | 61eaf1e15fcc370068978971 | Sanika Tamhankar | 61eaf1de9d17400069023706 | Sanika Tamhankar | 61eaf1de9d17400069023706 | 2022-03-16 21:46 | 2022-04-02 20:56 | 2022-04-03 13:44 |  |  | 0 | [5 empty] | Sanika Tamhankar | 61eaf1de9d17400069023706 | [22 empty] | {} |  | 0¦i000dj: | TMP Sprint 5 |  | 4 |  | 10000 | Trip Management - Web Application | In Progress
Ride sharing billing back-end | TMP-59 | 10058 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Dharmay Sureja | 61eaf1e15fcc370068978971 | Prakrut Suthar | 61eafca5e2261a0069599b93 | Prakrut Suthar | 61eafca5e2261a0069599b93 | 2022-03-04 15:29 | 2022-04-02 17:35 | 2022-04-03 13:44 | 2022-04-02 17:35 |  | 0 | [5 empty] | Prakrut Suthar | 61eafca5e2261a0069599b93 | [22 empty] | {} |  | 0¦i0008g:x | TMP Sprint 4 |  | 5 |  | 10000 | Trip Management - Web Application | Done
Payment Module Backend and API | TMP-46 | 10045 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Dharmay Sureja | 61eaf1e15fcc370068978971 | amudgal | 61f7ee1aaab3620070f4b803 | Sanika Tamhankar | 61eaf1de9d17400069023706 | 2022-03-01 19:33 | 2022-03-16 22:05 | 2022-03-03 18:54 | 2022-03-16 22:05 |  | 0 | Functionality |  |  | This Story is created for Payment module functionality(Backend and API). It involves the development of Tables, Queries and API calls for the payment module in the Trip Management application. |  | Sanika Tamhankar | 61eaf1de9d17400069023706 | ;16/Mar/22 10:02 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;14400 | ;16/Mar/22 10:03 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;14400 | ;16/Mar/22 10:03 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;3600 | ;16/Mar/22 10:03 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;7200 | ;16/Mar/22 10:04 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;7200 | ;16/Mar/22 10:04 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;14400 | ;16/Mar/22 10:04 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;14400 | ;16/Mar/22 10:04 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;10800 | [6 empty] | 0 | 86400 |  |  | 0 | 86400 |  | Appropriate queries should be developed and implemented in the projectâ€™s source code. API calls must be developed and tested for the payment module. | {} |  | 0¦i0009v: | TMP Sprint 3 |  | 3 |  | 10000 | Trip Management - Web Application | Done
User Interface for the Authentication Module | TMP-33 | 10032 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Dharmay Sureja | 61eaf1e15fcc370068978971 | amudgal | 61f7ee1aaab3620070f4b803 | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-02-15 18:24 | 2022-03-01 20:05 | 2022-03-01 23:21 | 2022-03-01 20:05 |  | 0 | User_Interface |  |  |  |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | ;01/Mar/22 8:04 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;10800 | ;01/Mar/22 8:04 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;10800 | ;01/Mar/22 8:04 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;10800 | ;01/Mar/22 8:05 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;7200 | ;01/Mar/22 8:05 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;10800 | ;01/Mar/22 8:05 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;7200 | [8 empty] | 0 | 57600 |  |  | 0 | 57600 |  | A basic functional login screen should be displayed. | {} |  | 0¦i0001i: | TMP Sprint 2 |  | 2 |  | 10000 | Trip Management - Web Application | Done
Create and Maintain a Database for the application | TMP-27 | 10026 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Dharmay Sureja | 61eaf1e15fcc370068978971 | Ankush Mudgal | 61f07bf2138863006aa1d85f | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-02-15 18:00 | 2022-03-01 19:46 | 2022-03-01 23:21 | 2022-03-01 19:46 |  | 0 | Database |  |  | Creating Database and tables from the database design |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | Data base connection and table creation;16/Feb/22 10:25 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;7200 | ;22/Feb/22 5:37 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;3600 | ;22/Feb/22 5:37 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;3600 | ;22/Feb/22 5:37 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;10800 | ;22/Feb/22 5:38 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;10800 | ;28/Feb/22 6:01 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;10800 | ;28/Feb/22 6:01 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;10800 | [7 empty] | 0 | 57600 |  |  | 0 | 57600 |  | This story is internal to the Dev team, and the client team has no acceptance criteria for it. | {} |  | 0¦i0006b: | TMP Sprint 2 |  | 2 |  | 10000 | Trip Management - Web Application | Done
Setting up a Code Repository on GitLab | TMP-2 | 10001 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Dharmay Sureja | 61eaf1e15fcc370068978971 | amudgal | 61f7ee1aaab3620070f4b803 | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-01-31 10:18 | 2022-02-15 01:37 | 2022-02-03 00:34 | 2022-02-15 01:37 |  | 0 | Configuration |  |  | User Story for the creation of a repository titled â€œTrip Management Systemâ€ in GitLab |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | ;03/Feb/22 6:58 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;7200 | ;03/Feb/22 6:59 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;10800 | ;03/Feb/22 6:59 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;3600 | ;10/Feb/22 7:01 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;7200 | ;10/Feb/22 7:02 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;10800 | ;10/Feb/22 7:02 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;7200 | ;10/Feb/22 7:03 PM;ug:81340c97-e339-4961-a4a6-23b98c8b7786;7200 | [7 empty] | 0 | 54000 |  |  | 0 | 54000 |  | A Repository to store all related code and documents for the project is successfully set up on GitLab with appropriate privileges and user access. | {} |  | 0¦i0000e:i | TMP Sprint 1 |  | 2 |  | 10000 | Trip Management - Web Application | Done
Develop and Execute Test cases for the Application | TMP-80 | 10079 | Story | In Progress | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium |  | Prakrut Suthar | 61eafca5e2261a0069599b93 | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-03-21 15:11 | 2022-04-02 20:56 | 2022-04-03 13:41 |  |  | 0 | [5 empty] | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | [22 empty] | {} |  | 0¦i000dx: | TMP Sprint 5 |  | 4 |  | 10000 | Trip Management - Web Application | In Progress
Refactor Unit Testing and Integration test of Ride share module | TMP-65 | 10064 | Story | In Progress | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium |  | Prakrut Suthar | 61eafca5e2261a0069599b93 | Sanika Tamhankar | 61eaf1de9d17400069023706 | Sanika Tamhankar | 61eaf1de9d17400069023706 | 2022-03-16 21:49 | 2022-04-02 20:56 | 2022-04-03 13:44 |  |  | 0 | [5 empty] | Sanika Tamhankar | 61eaf1de9d17400069023706 | [22 empty] | {} |  | 0¦i000dr: | TMP Sprint 5 |  | 4 |  | 10000 | Trip Management - Web Application | In Progress
Notification for ride sharing module | TMP-58 | 10057 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Prakrut Suthar | 61eafca5e2261a0069599b93 | Prakrut Suthar | 61eafca5e2261a0069599b93 | Prakrut Suthar | 61eafca5e2261a0069599b93 | 2022-03-04 15:28 | 2022-04-02 17:35 | 2022-04-03 13:44 | 2022-04-02 17:35 |  | 0 | [5 empty] | Prakrut Suthar | 61eafca5e2261a0069599b93 | [22 empty] | {} |  | 0¦i0008h: | TMP Sprint 4 |  | 4 |  | 10000 | Trip Management - Web Application | Done
User Interface for Ride Share module for Customer | TMP-43 | 10042 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Prakrut Suthar | 61eafca5e2261a0069599b93 | Ankush Mudgal | 61f07bf2138863006aa1d85f | Sanika Tamhankar | 61eaf1de9d17400069023706 | 2022-03-01 19:31 | 2022-03-17 00:04 | 2022-04-03 13:44 | 2022-03-17 00:04 |  | 0 | API | User_Interface |  | The story is created for Ride share User interface for Customer |  | Sanika Tamhankar | 61eaf1de9d17400069023706 | ;16/Mar/22 11:56 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;7200 | ;16/Mar/22 11:56 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;7200 | ;16/Mar/22 11:56 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;7200 | ;16/Mar/22 11:58 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;14400 | ;16/Mar/22 11:58 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;14400 | ;17/Mar/22 12:00 AM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;10800 | ;17/Mar/22 12:00 AM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;14400 | ;17/Mar/22 12:04 AM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;10800 | [6 empty] | 0 | 86400 |  |  | 0 | 86400 |  |  | {} |  | 0¦i0008v: | TMP Sprint 3 |  | 3 |  | 10000 | Trip Management - Web Application | Done
Design and develop an User Interface for Vehicle Management. | TMP-32 | 10031 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Prakrut Suthar | 61eafca5e2261a0069599b93 | Ankush Mudgal | 61f07bf2138863006aa1d85f | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-02-15 18:17 | 2022-03-01 19:28 | 2022-03-01 23:21 | 2022-03-01 19:28 |  | 0 | API | Functionality | User_Interface | Developing front end user interface for management module. Design and create an interface for vehicle management. |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | ;17/Feb/22 6:46 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;7200 | ;21/Feb/22 10:54 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;7200 | ;21/Feb/22 10:55 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;7200 | ;21/Feb/22 10:55 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;14400 | ;28/Feb/22 5:56 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;14400 | ;28/Feb/22 5:58 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;7200 | ;28/Feb/22 5:58 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;7200 | ;28/Feb/22 5:59 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;14400 | ;28/Feb/22 6:01 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;7200 | [5 empty] | 0 | 86400 |  |  | 0 | 86400 |  | A basic interface with all the details about an individual vehicle(for eg km traveled, fuel used so far) should be displayed. | {} |  | 0¦i00067: | TMP Sprint 2 |  | 3 |  | 10000 | Trip Management - Web Application | Done
Create Database design | TMP-5 | 10004 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Prakrut Suthar | 61eafca5e2261a0069599b93 | amudgal | 61f7ee1aaab3620070f4b803 | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-01-31 10:26 | 2022-02-11 20:10 | 2022-02-03 00:34 | 2022-02-10 19:03 |  | 0 | Configuration |  |  | User Story for the creation of a database design. |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | ;07/Feb/22 9:11 AM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;7200 | ;10/Feb/22 7:01 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;7200 | ;10/Feb/22 7:02 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;7200 | ;10/Feb/22 7:03 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;3600 | ;10/Feb/22 7:03 PM;ug:2fdd02ff-3950-4229-8fe6-7dccad182104;3600 | [9 empty] | 0 | 28800 |  |  | 0 | 28800 |  | Database design including possible entities, attributes are identified and presented to the client | {} |  | 0¦i0000e: | TMP Sprint 1 |  | 3 |  | 10000 | Trip Management - Web Application | Done
Bug Fixes backend | TMP-66 | 10065 | Story | In Progress | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium |  | Sanika Tamhankar | 61eaf1de9d17400069023706 | Sanika Tamhankar | 61eaf1de9d17400069023706 | Sanika Tamhankar | 61eaf1de9d17400069023706 | 2022-03-21 14:40 | 2022-04-02 20:56 | 2022-04-03 13:44 |  |  | 0 | [5 empty] | Sanika Tamhankar | 61eaf1de9d17400069023706 | [22 empty] | {} |  | 0¦i000dn: | TMP Sprint 5 |  | 4 |  | 10000 | Trip Management - Web Application | In Progress
Ride Share creation Backend and API for VehicleOwner | TMP-63 | 10062 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Sanika Tamhankar | 61eaf1de9d17400069023706 | Sanika Tamhankar | 61eaf1de9d17400069023706 | Sanika Tamhankar | 61eaf1de9d17400069023706 | 2022-03-16 21:42 | 2022-04-01 16:53 | 2022-04-03 13:44 | 2022-04-01 16:53 |  | 0 | [5 empty] | Sanika Tamhankar | 61eaf1de9d17400069023706 | ;01/Apr/22 4:50 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;10800 | ;01/Apr/22 4:50 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;240 | ;01/Apr/22 4:50 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;14400 | ;01/Apr/22 4:50 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;10800 | ;01/Apr/22 4:50 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;14400 | ;01/Apr/22 4:51 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;14400 | ;01/Apr/22 4:51 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;21600 | ;01/Apr/22 4:51 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;7200 | ;01/Apr/22 4:51 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;10800 | ;01/Apr/22 4:51 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;10800 | ;01/Apr/22 4:52 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;3360 | ;01/Apr/22 4:52 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;18000 | ;01/Apr/22 4:52 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;7200 |  | 0 | 144000 |  |  | 0 | 144000 |  |  | {} |  | 0¦i0008i: | TMP Sprint 4 |  | 5 |  | 10000 | Trip Management - Web Application | Done
Ride sharing billing UI | TMP-60 | 10059 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Sanika Tamhankar | 61eaf1de9d17400069023706 | Prakrut Suthar | 61eafca5e2261a0069599b93 | Prakrut Suthar | 61eafca5e2261a0069599b93 | 2022-03-04 15:29 | 2022-04-01 16:54 | 2022-04-03 13:44 | 2022-04-01 16:54 |  | 0 | [5 empty] | Prakrut Suthar | 61eafca5e2261a0069599b93 | ;01/Apr/22 4:53 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;21600 | ;01/Apr/22 4:53 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;21600 | ;01/Apr/22 4:53 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;28800 | ;01/Apr/22 4:54 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;14400 | [10 empty] | 0 | 86400 |  |  | 0 | 86400 |  |  | {} |  | 0¦i0008g:r | TMP Sprint 4 |  | 3 |  | 10000 | Trip Management - Web Application | Done
Notification Module for authentication | TMP-42 | 10041 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Sanika Tamhankar | 61eaf1de9d17400069023706 | Ankush Mudgal | 61f07bf2138863006aa1d85f | Sanika Tamhankar | 61eaf1de9d17400069023706 | 2022-03-01 19:31 | 2022-03-16 21:39 | 2022-04-03 13:44 | 2022-03-16 21:39 |  | 0 |  |  |  | The story is created for the Notification module where the User will get notification on for login |  | Sanika Tamhankar | 61eaf1de9d17400069023706 | ;16/Mar/22 9:37 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;10800 | ;16/Mar/22 9:38 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;10800 | ;16/Mar/22 9:38 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;10800 | ;16/Mar/22 9:38 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;14400 | ;16/Mar/22 9:38 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;14400 | ;16/Mar/22 9:38 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;18000 | [8 empty] | 0 | 79200 |  |  | 0 | 90000 |  |  | {} |  | 0¦i0008n: | TMP Sprint 3 |  | 3 |  | 10000 | Trip Management - Web Application | Done
User Login Backend and Api | TMP-6 | 10005 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Sanika Tamhankar | 61eaf1de9d17400069023706 | Ankush Mudgal | 61f07bf2138863006aa1d85f | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-01-31 10:27 | 2022-03-01 19:29 | 2022-03-01 23:22 | 2022-03-01 19:29 |  | 0 | API | Database |  | * Login * Registration. * Forget password |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | ;17/Feb/22 12:31 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;3600 | ;17/Feb/22 12:31 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;3600 | ;01/Mar/22 7:27 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;10800 | ;01/Mar/22 7:27 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;10800 | ;01/Mar/22 7:28 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;7200 | ;01/Mar/22 7:28 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;7200 | ;01/Mar/22 7:28 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;3600 | ;01/Mar/22 7:28 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;7200 | ;01/Mar/22 7:29 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;7200 | ;01/Mar/22 7:29 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;14400 |  |  |  |  | 0 | 75600 |  |  | 0 | 93600 |  | Login page for User is working properly | {} |  | 0¦i0006r: | TMP Sprint 2 |  | 3 |  | 10000 | Trip Management - Web Application | Done
Create project architecture skeleton | TMP-4 | 10003 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Sanika Tamhankar | 61eaf1de9d17400069023706 | amudgal | 61f7ee1aaab3620070f4b803 | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-01-31 10:26 | 2022-02-14 19:44 | 2022-02-03 00:34 | 2022-02-14 19:44 |  | 0 | Configuration |  |  | Story for creating a project skeleton including test controller, dao, service and model. |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | ;02/Feb/22 9:28 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;14400 | ;10/Feb/22 4:44 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;7200 | ;10/Feb/22 4:44 PM;ug:03b1ec25-c1cc-496d-97f4-d3d9f07df753;3600 | [11 empty] | 0 | 25200 |  |  | 0 | 82860 |  | Project skeleton including test controller, dao, service and model are created and are working for test data. | {} |  | 0¦i0000e:4 | TMP Sprint 1 |  | 3 |  | 10000 | Trip Management - Web Application | Done
Bug Fixes - UI | TMP-67 | 10066 | Story | In Progress | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium |  | Vatsal Yadav | 61eaf1e0eb1fb60071cf9d29 | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-03-21 14:40 | 2022-04-02 20:56 | 2022-04-01 18:09 |  |  | 0 |  |  |  | Parent Story to track bug fixes relevant to UI. |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | [22 empty] | {} |  | 0¦i000dp: | TMP Sprint 5 |  | 4 |  | 10000 | Trip Management - Web Application | In Progress
User Interface for Ride Share module for Customer | TMP-62 | 10061 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Vatsal Yadav | 61eaf1e0eb1fb60071cf9d29 | Sanika Tamhankar | 61eaf1de9d17400069023706 | Sanika Tamhankar | 61eaf1de9d17400069023706 | 2022-03-16 21:41 | 2022-03-27 14:02 | 2022-04-03 13:44 | 2022-03-27 14:02 |  | 0 | [5 empty] | Sanika Tamhankar | 61eaf1de9d17400069023706 | [22 empty] | {} |  | 0¦i0008g:v | TMP Sprint 4 |  | 3 |  | 10000 | Trip Management - Web Application | Done
Resolve Heroku UI Issue with Thymeleaf | TMP-47 | 10046 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Vatsal Yadav | 61eaf1e0eb1fb60071cf9d29 | Ankush Mudgal | 61f07bf2138863006aa1d85f | Sanika Tamhankar | 61eaf1de9d17400069023706 | 2022-03-01 19:52 | 2022-03-04 17:08 | 2022-04-03 13:44 | 2022-03-04 17:08 |  | 0 |  |  |  | This story is related to the previous sprint story [https://csci5308-group16.atlassian.net/browse/TMP-24¦https://csci5308-group16.atlassian.net/browse/TMP-24¦smart-link]. The aim is to resolve an issue we are facing. |  | Sanika Tamhankar | 61eaf1de9d17400069023706 | [22 empty] | {} |  | 0¦i0009r: | TMP Sprint 3 |  | 1 |  | 10000 | Trip Management - Web Application | Done
UI for Payment Module | TMP-45 | 10044 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Vatsal Yadav | 61eaf1e0eb1fb60071cf9d29 | Sanika Tamhankar | 61eaf1de9d17400069023706 | Sanika Tamhankar | 61eaf1de9d17400069023706 | 2022-03-01 19:33 | 2022-04-02 17:28 | 2022-04-02 17:44 | 2022-04-02 17:28 |  | 0 |  |  |  | This story is created for Payment module User Interface |  | Sanika Tamhankar | 61eaf1de9d17400069023706 | [22 empty] | {} |  | 0¦i0008g: | TMP Sprint 4 |  | 3 |  | 10000 | Trip Management - Web Application | Done
Ride Share Booking creation Backend and API for Customer | TMP-44 | 10043 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Vatsal Yadav | 61eaf1e0eb1fb60071cf9d29 | Ankush Mudgal | 61f07bf2138863006aa1d85f | Sanika Tamhankar | 61eaf1de9d17400069023706 | 2022-03-01 19:32 | 2022-03-17 00:05 | 2022-04-03 13:44 | 2022-03-17 00:05 |  | 0 |  |  |  | This story is created for Rideshare module functionality for customer (Backend and API) |  | Sanika Tamhankar | 61eaf1de9d17400069023706 | [22 empty] | {} |  | 0¦i00093: | TMP Sprint 3 |  | 2 |  | 10000 | Trip Management - Web Application | Done
Create a dashboard for accessing information relevant to vehicles | TMP-28 | 10027 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Vatsal Yadav | 61eaf1e0eb1fb60071cf9d29 | Ankush Mudgal | 61f07bf2138863006aa1d85f | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-02-15 18:03 | 2022-03-01 19:23 | 2022-03-01 23:20 | 2022-03-01 19:23 |  | 0 | Database |  |  |  |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | [21 empty] | A dashboard is presented with all the details of the vehicles owned by that user. | {} |  | 0¦i0001h: | TMP Sprint 2 |  | 3 |  | 10000 | Trip Management - Web Application | Done
Setting up the Server on Heroku | TMP-24 | 10023 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Vatsal Yadav | 61eaf1e0eb1fb60071cf9d29 | Ankush Mudgal | 61f07bf2138863006aa1d85f | Sanika Tamhankar | 61eaf1de9d17400069023706 | 2022-02-11 20:53 | 2022-03-01 19:22 | 2022-03-01 23:22 | 2022-03-01 19:22 |  | 0 |  |  |  | Setting up the server |  | Sanika Tamhankar | 61eaf1de9d17400069023706 | [18 empty] | 7200 | 21600 |  | Server is up and running | {} |  | 0¦i0001f: | TMP Sprint 2 |  | 2 |  | 10000 | Trip Management - Web Application | Done
Create an initial File Hierarchy | TMP-7 | 10006 | Story | Done | TMP | Trip_Management | software | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 |  | Medium | Done | Vatsal Yadav | 61eaf1e0eb1fb60071cf9d29 | amudgal | 61f7ee1aaab3620070f4b803 | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | 2022-01-31 10:29 | 2022-02-14 16:20 | 2022-02-10 18:54 | 2022-02-14 16:20 |  | 0 | Configuration |  |  | Story for Creating initial project file or the base of the file. |  | Benny Daniel T. | 61eaf0597ae0dc006ac957d6 | [14 empty] | 0 |  |  |  | 7200 | 90000 |  | The base of the project files is created | {} |  | 0¦i0000d: | TMP Sprint 1 |  | 3 |  | 10000 | Trip Management - Web Application | Done